## Summary
DML Extraction to postdbscripts - Status Report
Repository: apha-fps-apps ¦ Folder: dbscript/liquibase
Generated: 2026-09-27
Overview
Metric | Count
Changesets reviewed for DML content | 22
Pure-DML files moved whole to postdbscripts | 7
Mixed DDL+DML files reviewed | 15
Mixed files split (safe DML extracted) | 5
Mixed files kept fully in changesets (unsafe to split) | 10
New postdbscripts CR files created | 12
Pending / follow-up actions | 3
Key risk to flag to deployment owners
Liquibase identifies a changeset by id+author+filepath. Files/statements moved out of changesets/ into postdbscripts/ will look unrun in environments where the original changeset already executed, and may run again next deploy. Every moved/extracted item was verified to be idempotent (ON CONFLICT / WHERE NOT EXISTS / time-based conditions), so re-running is harmless.

## Pure DML - Moved
Original file (changesets/) | New location (postdbscripts/) | Content | Status | Action pending
006_batchjobs_seed_data.sql | postdbscripts/006_batchjobs_seed_data.sql | Seeds job_master + job_status for RecreateSummary, MABArchive, FECProcess, YearEndProcess | Done | None
cr017_seed_data_fps_job_status.sql | postdbscripts/cr017_seed_data_fps_job_status.sql | Deletes 'Cancelled' status from seed data | Done | None
cr019_seed_data_job_master.sql | postdbscripts/cr019_seed_data_job_master.sql | Renames job 'RecreateSummaries' to 'RecreateSummary' | Done | None
cr031_delete_seeddata_jobstatus_jobmaster.sql | postdbscripts/cr031_delete_seeddata_jobstatus_jobmaster.sql | Removes YearEndProcess job/status seed rows | Done | None
cr033_seed_tblyearmaster_data.sql | postdbscripts/cr033_seed_tblyearmaster_data.sql | Seeds tblyearmaster rows for FPS years 2016-2026 | Done | None
cr048_seed_yearend_datasetup_cutover_jobs.sql | postdbscripts/cr048_seed_yearend_datasetup_cutover_jobs.sql | Seeds YearEnd-DataSetup / YearEnd-CutOver jobs and statuses | Done | None
cr075_seed_account_codes.sql | postdbscripts/cr075_seed_account_codes.sql | Seeds default account code / sub-account code rows | Done | None

## Mixed - Split
Original changeset (changesets/) | Extracted DML new file (postdbscripts/) | What was extracted | Why it was safe to split | Status | Action pending
cr026_modify_ddl_batchjobs.sql | postdbscripts/cr026_cleanup_stale_jobs_and_locks.sql | Trailing stale job/lock reconciliation (UPDATE + DELETE) | Runs after all new columns already exist in the file; nothing later depends on it | Done | None
cr028_add_constraint_job_queue.sql | postdbscripts/cr028_cleanup_job_lock.sql | The already-separate 'CR028_cleanup' changeset (stale lock DELETE) | Was already isolated as its own changeset id; time-based cleanup only | Done | None
cr044_bulk_rates_jobs_staging_and_validation.sql | postdbscripts/cr044_seed_bulk_rates_jobs.sql | Leading job_master/job_status seed rows for 3 Bulk Rates jobs | Seeds pre-existing tables; unrelated to the staging tables created later in the file | Done | None
cr047_milestone_notifications_job_and_audit.sql | postdbscripts/cr047_seed_milestone_notifications_job.sql | Leading job_master/job_status seed row for MilestoneUpdateNotifications | Same reasoning as cr044 | Done | None
cr073_create_masterlookup_and_directorate.sql | postdbscripts/cr073_seed_masterlookup.sql | tblmasterlookup seed (DELETE + 3 INSERTs) | Unrelated to the tbldirectorate FK work later in the same file | Done | None

## Mixed - Kept Whole
Changeset (changesets/) | Why the DML can't be separated | Status | Action pending
cr032_modify_fps_tblstagingmonthlytime.sql | Backfills the new 'id' column before it is made NOT NULL and turned into the primary key | Kept - no action | None - re-review only if the table structure changes again
cr034_convert_money_columns_to_numeric_19_4.sql | The DML is procedural bookkeeping (temp tables tracking view dependencies) for an in-place type conversion algorithm, not business data | Kept - no action | None
cr043_projectmonthcasework_fpsyear_and_indexes.sql | Backfills fpsyear before it is made NOT NULL and the primary key is replaced | Kept - no action | None | check if we can partial move this to postdb scripts
cr045_job_queue_upload_metadata_and_bulk_rates_download.sql | Migrates data from the old configuration_json column into new columns inside the same ALTER TABLE block | Kept - no action | None | check if we can partial move this to postdb scripts
cr073_create_masterlookup_and_directorate.sql (directorate part only) | The tbldirectorate seed INSERT must run before the ADD CONSTRAINT FK later in the file, otherwise FK creation fails against an empty table | Kept - no action | None | check if we can partial move this to postdb scripts by adding if not exists
cr071_partition_audit_tables.sql | Copies data into new partitioned/shadow tables, verifies row-count parity, then renames tables - the copy must happen between create and swap in the same changeset | Kept - no action | None | Ask Arihant to review postdbscripts
cr077_partition_job_queue_log.sql | Same partition create -> copy -> verify -> swap pattern as cr071 | Kept - no action | None | Ask Arihant to review postdbscripts
cr082_partition_period_timecostcalcs.sql | Same partition create -> copy -> verify -> swap pattern as cr071 | Kept - no action | None | Ask Arihant to review postdbscripts
cr083_partition_period_proj_subcontract.sql | Same partition create -> copy -> verify -> swap pattern as cr071 | Kept - no action | None | Ask Arihant to review postdbscripts
cr084_partition_period_monthlyoutput.sql | Same partition create -> copy -> verify -> swap pattern as cr071 | Kept - no action | None | Ask Arihant to review postdbscripts
cr085_partition_projectmonthcasework.sql | Same partition create -> copy -> verify -> swap pattern as cr071 | Kept - no action | None | Ask Arihant to review postdbscripts

## Pending Actions
# | Action | Owner | Why it matters | Status
1 | Confirm Dev/SIT/Production deployment plan for re-running the 12 relocated/extracted changesets under their new ids/paths | Deployment owner | Liquibase will treat them as new changesets at their new file path and may execute them again on next deploy; all are idempotent so this is expected to be harmless, but should be communicated ahead of time | Pending decision
2 | Decide whether to also update the 5 original mixed changesets' rollback comments to reflect the removed DML (currently left as-is for historical accuracy) | Repo maintainer | Rollback comments in cr026/cr028/cr044/cr047/cr073 still describe the full original behaviour; not functionally required but could be tidied for clarity | Pending decision
3 | Review the 10 'kept whole' mixed changesets individually if their target tables are restructured again in future, to see if extraction becomes possible then | Repo maintainer | Not required now; documented so future changes don't have to re-derive the reasoning | Pending decision